## Slide 1: Education in Emergencies Monitoring Programmes

## Slide 2: Learning Objectives
Monitoring is a critical component of programme design and continuous monitoring will improve both accountability and quality.
As an essential part of the INEE minimum standards, monitoring is utilised to measure progress towards attaining the standards.
Monitoring can measure the progress, results and impact of programmes.
INEE and Global Education Cluster

## Slide 3: Monitoring
Monitoring is a process of tracking or measuring what is happening in programmes or activities being conducted. It includes measuring progress of an intervention and measuring change.
INEE and Global Education Cluster

## Slide 4: Purpose of Monitoring
To provide information to improve programme performance.
To provide accountability in terms of the implementation running according to plan.
To serve as an input to evaluation.
To aid broader advocacy efforts to strengthen policies and programmes aimed at the rights of children and women.
INEE and Global Education Cluster

## Slide 5: What does Monitoring Measure
The progress or output of the activity (e.g. schools are reopening, are children attending lessons, school tents have been erected).
The outcomes of the activity (enrolment rates have increased, learning is taking place in the classroom, children have increased knowledge on health and hygiene issues).
The impact of the activity (increased pass rates, a decrease in repeaters, less instances of diarrhoea etc).
Side effects (The unintended consequences of an intervention such as the stigmatisation of children).
INEE and Global Education Cluster

## Slide 6: Indicators
What are Indicators?
An indicator is an objective way of measuring progress through collecting factual information.
Indicators are measurable or tangible signs that something has been done or that something has been achieved.
Data collected about the indicator tells us if the expected change has happened.
Indicators should be sensitive to cross cutting issues such as gender and inclusiveness .
INEE and Global Education Cluster

## Slide 7: Monitoring Plan
Activity | Indicator | Time Period/ Frequency | Assumptions/ Risks | Key Stakeholders
Select two programme interventions.
Concentrate on the progress, outputs and outcomes of the interventions.
15 minutes.
INEE and Global Education Cluster

## Slide 8: Conclusions
Monitoring is a process of gathering information to measure whether an intervention has achieved its objectives.
Education indicators outline key quantitative measures of activities and programme initiatives.
The education sector/cluster supports the MoE to ensure the collection of quality and reliable monitoring data - used to identify gaps and target needs.
Monitoring is critical for measuring progress towards attaining the INEE minimum standards.
Continuous monitoring help improve programme accountability and quality.
INEE and Global Education Cluster