Education Cluster

FINAL

Education in Emergencies (EiE) Contingency Planning Workshop

Gokarna Resort

12-13 June 2009

Objectives of the workshop:

- Provide context and overview on the global humanitarian assistance, cluster mechanism and  minimum standards for education in emergencies.

- Identify lessons learned and best practices from the education cluster  emergency preparedness and responses activities during the Koshi/ Kailali and Kanchanpur floods in 2008 and how they meet or do not meet minimum standards for education in emergencies.

- Prepare  education in emergency contingency plan for 2009/10 in relation to agreed scenarios.

Expected outcomes

- Increased/broadened understanding on  the context of humanitarian assistance and  cluster mechanism.

- Understand the key principles of minimum standards for effective preparedness and response for education in emergencies.

- Successes, challenges and gaps in the preparedness and responses activities identified and key recommendations on the way forward formulated.

- Education in emergency contingency plan for 2009/10 revised based on lessons learned and identified recommendations.

Participants: Department of Education, District Education Officers, Regional Education Directorates, Plan Nepal, Save the Children, Nepal Red Cross Society, IFCD, Seto Gurans, UNICEF, World Education

Facilitators: 	George Murry, Disaster Response Advisor, OCHA

Sweta Shah, Inter-agency Network for Education in Emergencies (INEE)

Bhola Dahal, Save the Children

Lieke Van De Wiel, UNICEF

DAY ONE:

1. Welcome Remarks:

The welcome remarks were done by George Murray, Sweta Shah, Lieke Van De Wiel and Bhola Dahal.

Director General of Department of Education, Mr. Mahashram Sharma addressed that government usually delays in implementing the plans. The long process delays to response but this year a high hope is there that the government will support the contingency plan and this will also alert them to response and implement the plans on time.

2. Why Contingency Plan ? – George Murray

a) Introduction and Objectives

Three main things were highlighted in planning and there were Time, Needs and Coordination.

Interagency plan prepares global scenario and the clusters prepares their scenario according to it.

b) Phases of response

- Emergency Preparedness: actions taken in  anticipation of an emergency to facilitate rapid, effective and appropriate response

- Contingency Planning: process of establishing programme objectives, approaches and procedures to situations or events likely to occur, including identifying those events and developing likely scenarios and appropriate plans to prepare and response to them in an effective manner”

- Emergency Response : an organized set of actions taken to ensure the provision of appropriate emergency assistance to targeted vulnerable populations

c) Inter-agency Contingency Planning

- Common analysis of potential emergencies and their impact

- Common prioritization of potential emergencies

- Developing plans to deal with prioritised potential emergencies

- Division of labour among actors

- Ensuring necessary preparedness measures and follow-up actions are taken.

d) Key principles of Contingency Planning

- Practical (realistic and not bureaucratic exercise)

- Simple and easy to do – all staff should be able to participate

- Process driven – written product is important however without a process it is useless

- Participatory

- Resident Coordinator (RC)/Humanitarian Coordinator (HC) are responsible for the overall development and maintenance of contingency plans.

- Clusters (with Government and partners) are responsible for detailed response plans.

e) Why Contingency Planning? Benefits

- Ensures a responsive decision-making mechanism within the humanitarian family. Allows for a proactive system for disaster response coordination among all partners.

- Ensures the availability of resources and their effective mobilization for phased response

- Linkages and arrangements are established and commitments secured before any disaster occurs

- Maximizes cost effectiveness.

- Avoids duplication.

Role of local communities in planning:

- Local Communities are incredible for implementation of the plans. If any emergency arises then local community will be required for the response. Emergency preparedness for plan is being developed and these plans are developed by local level.

- Communities’ plans are very important. This year workshop was organized by Ministry of Home and seven pilot contingency plans are being prepared in flood as major issue.

- Inviting locals for planning has always been an effective experience and we should encourage it in contingency planning as well.

3. a) Context Overview – Nepal Context – Helen Sherpa

- Before 2000 there was no contingency plan. Long after crisis we tried to solve out the post emergency problems.

- Importance of planning was realized from Makwanrpur  conflict. Pre-position the materials like text books,  baby pack etc. was also in priority but it did not work later because of lack of materials and storage during monsoon.

- Media criticism in past experience. We need to make sure we notice the major scenario.

- In 2005 contingency planning and CAP (Consolidated Appeal Process) was started.

- In 2006 funds were allocated and UNICEF hired a technical person for education in emergencies (Ms. Melinda Smith).

- In 2008 assessment and other tools were improved, tested and refined. Education in Emergencies trainings were conducted in Nepalgunj, Pokhara and Biratnagar in collaboration with the Child Protection cluster.

- Materials used have been translated and used.

- Lack of documentation of the process and experience have always been felt lacking and most important.

- Staff turnover and lack of dedicated people specifically for emergencies has made it difficult to sustain the group.

3. b. Hari Lamsal – DoE context of EiE from governments’ perspective

- No extra budget allocation for Education in Emergency in government.

- Coordination required at all levels.

- Teacher support and mobilization is the most difficult in government.

4. Humanitarian and cluster overview – George Murray

a) Humanitarian Response System:

It is an overarching principle.

“Each State has the responsibility first and foremost to take care of the victims of natural disasters and other emergencies occurring on its territory. Hence, the affected State has the primary role in the initiation, organization, coordination, and implementation of humanitarian assistance within its territory.”

b) Some Findings from the 2005 Humanitarian Response Review

- Well-known, long-standing gaps

- Limited linkages between UN and non-UN actors

- Coordination erratic and dependent on personalities

- Insufficient accountability (particularly for IDPs)

- Donor policies inconsistent

c) Changing Environment for humanitarian operations

- Proliferation of humanitarian actors

- Changing role of the UN (less direct implementation, more standard-setting and facilitation)

- Competitive funding environment

- Increased public scrutiny of humanitarian action

d) Four Pillars of Reform

CLUSTER APPROACH

Adequate capacity and predictable leadership in all sectors

HUMANITARIAN COORDINATORS

Effective leadership and coordination in humanitarian emergencies

HUMANITARIAN FINANCING

Adequate, timely and flexible financing

PARTNERSHIP

Strong partnerships between UN and non-UN actors

e) A Holistic Approach

PARTNERSHIPS

CAPACITY  & PREDICTABAILITY

FINANCING

LEADERSHIP

STRENGTHENING HUMANITARIAN RESPONSE

f) Aim of the Cluster Approach

- High standards of predictability, accountability and partnership in all sectors or areas of activity

- More strategic responses

- Better prioritization of available resources

g) When do we use the cluster approach?

In the event of a sudden major new emergency requiring a multi-sectoral response with the participation of a wide range of international humanitarian actors, the cluster approach should be used from the start in planning and organizing the international response.

h) Activation for Major New Emergency

Within the first 24 hours

- Humanitarian Coordinator (HC) (or Resident Coordinator - RC) consults relevant partners, proposes leads for each major sector/cluster

- HC/RC sends proposal to Emergency Response Coordination (ERC)

- Emergency Response Coordinator (ERC) shares proposal with Global Cluster Leads

Within 24 hours of receiving proposal from HC

- ERC ensures agreement at global level

- ERC communicates agreement to HC and partners

- HC (or RC) informs host government and all partners

i) Global Cluster Leads

Cluster/Sector Working Group

- Agriculture

- Camp Coordination/ Management

- Early Recovery

- Education in Emergencies

- Emergency Shelter

- Emergency Telecommunications

- Health

- Logistics

- Nutrition

- Protection

- Water, Sanitation & Hygiene

Global Cluster Leads

- FAO

- UNHCR & IOM

- UNDP

- UNICEF & Save the Children

- UNHCR & IFRC (Convenor)

- UNICEF & WFP

- WHO

- WFP

- UNICEF

- UNHCR, OHCHR, UNICEF

- UNICEF

* Agriculture and Education has been added in the cluster working groups.

j) Responsibilities of Global Cluster Leads

- Standard setting and consolidation of ‘best practice’

Build Response Capacity

  - Training and system development

  - Surge capacity and standby rosters

  - Material stockpiles

Operational Support

- Emergency preparedness

- Access to expertise

- Policies

- Advocacy and resource mobilization

k) Responsibilities of Cluster Leads at Country Level

- Establishment of appropriate coordination mechanisms

- Inclusion of key humanitarian partners

- Coordination with national/local authorities

- Needs assessment and analysis

- Planning and strategy development

- Application of standards

- Attention to priority cross-cutting issues

- Monitoring and reporting

- Advocacy and resource mobilization

- Emergency preparedness

- Training and capacity building

- Provision of assistance and services as a last resort

l) Relationship between Clusters at Country and Global Level

- Global cluster leads are accountable to the ERC for carrying out their TORs.

- Field cluster leads do not report to GCLs they report to the HC.

- Field clusters should use the GCLs as a resource.

- e.g. advice on global standards; policies and best practice; as well as for operational support; general guidance and training programmes.

m) Predictability, Accountability and Partnership in All Response Sectors

- Better support to national-led response efforts

- Common standards and tools

- Predictable stockpiles and trained expertise

- Unified interface for Governments, donors & other actors

- “First port of call” and “provider of last resort”

n) Clusters at local level

- Lead organizations may not be available at local level but cluster agencies may work closely in partnership with government and other locally available organizations.

- Many clusters are available at local level such as child protection, mine action, psychosocial care, gender etc.

- Before Home Ministry was the focal point for any emergency but now they are requesting to draft a letter at district level to have a focal person in each local level organization.

- At district level there is a separate DDRC in leadership of CDO to coordinate with all agencies.

5. Global Education Cluster – Sweta Shah

a)Education Cluster: Vision Statement

To enable all children and young people to have immediate access or ensured continuity to a quality education in a safe environment, in order to protect, develop and facilitate a return to normality and stability – through strengthened systems and tools that improve preparedness and response and facilitate effective partnership and action in the field.

Only cluster at global level co-led by UNICEF and Save the Children, with a Unit set up in Geneva

b) Education Cluster: Objectives

- Promote increased understanding of role of education in first phase and subsequent phases of emergency response and early recovery

- Promote and improve internationally recognised standards of good     practice in education

- Co-ordinate participating agencies in providing a rapid and effective response to education needs of children and young people affected by emergencies

- Strengthen response capacity through global pool of specialists skilled and experienced in ed in emergencies

- Promote increased understanding of role of education in first phase and subsequent phases of emergency response and early recovery

- Promote and improve internationally recognised standards of good     practice in education

- Co-ordinate participating agencies in providing a rapid and effective response to education needs of children and young people affected by emergencies

- Strengthen response capacity through global pool of specialists skilled and experienced in ed in emergencies

c) Four Task Teams

- Field Operations (chaired by: UNICEF and Save the Children)

Developing and strengthening systems for deployment of human and material resources (including developing a field guidance for cluster coordinators)

- Capacity Building (chaired by: UNICEF and Save the Children)

Developing training materials and assisting in training or all education stakeholders from UN and NGO staff to ministry of education officials

- Knowledge Management (chaired by: INEE, WFP, Save the Childrenb)

Collection and rapid dissemination of assessment information that accurately defines the needs, maps existing resources, and identifies gaps and priorities in the field of education in emergencies

- Global Oversight, Advocacy and Liason (chaired by: UNESCO and UNICEF)

- Maintains global oversight and accountability over Global Education Cluster.

- Finalizes the annual work plan budget, appeals and advocacy.

- Also maintains connections with other clusters and networks.

6. 	a) Minimum Standards for Education in Emergencies, Chronic Crises and 	Early Reconstruction – Sweta Shah

- Inter-agency Network for Education in Emergencies (INEE) is an open network of UN agencies, NGOs, donors, practitioners, researchers and individuals from affected populations (4 staff, interns, consultants and volunteers)

- Working to ensure right to education in emergencies and post-crisis reconstruction

- Sharing good practices, tools and research

- Encouraging information sharing among members and partners

www.ineesite.org

b) Why develop Education Minimum Standards?

- SPHERE (www.sphereproject.org) began in 1997 to address concerns of quality and accountability in humanitarian responses

- Minimum Standards in Disaster Response

- Water, sanitation and hygiene promotion

- Food security, nutrition and food aid

- Shelter, settlement and non-food items

- Health services

- But No Education

c) Goal of the INEE Minimum Standards

- Common starting point to reach a minimum level of educational quality and access

- Tool to improve coordination and enhance accountability and predictability

- Tool for capacity-building and training

- Aid to strengthen the resilience of Ministries of Education

d) What are Standards ?

- What are Standards?

  - Goals to be met

  - Practical guide to plan and develop appropriate educational responses

  - Ensure all components of education are included

e) The INEE Minimum Standards Categories

Community Participation -- Analysis -- Community Participation -- Analysis --

Access & Learning Environment

Teaching & Learning

Teachers & Other Education Personnel

Education Policy & Coordination

Cross cutting issues:

- Human and children’s rights

- Gender

- HIV/AIDS

- Disability and vulnerability

f) Community Participation

- Standard 1: (Active Participation) Community members actively participate in assessing, planning, implementing, monitoring and evaluating the education program.

- Standard 2: (Resources) Local community resources are identified, mobilized and used to implement education programs and other learning activities.

g) Analysis

- Standard 1: (Initial Assessment) Assessment conducted in a holistic and participatory way.

- Standard 2: (Response Strategy) Framework for education response developed, including a clear description of the problem and a documented strategy for action.

- Standard 3: (Monitoring) All relevant stakeholders regularly monitor education response activities and the evolving needs of the affected population.

- Standard 4: (Evaluation) Evaluation conducted in order to improve peace and enhance accountability.

h) Access and Learning Environment

- Standard 1: (Equal Access) All individuals have access to quality and relevant education opportunities.

- Standard 2: (Protection and Well-being) Learning environments are secure and promote the protection and mental and emotional well-being of learners.

- Standard 3: (Facilities) Education facilities are conducive to the physical well-being of learners.

i) Teaching and Learning

- Standard 1: (Curricula) Culturally, socially and linguistically relevant curricula are used.

- Standard 2: (Training) Teachers and other education personnel receive periodic, relevant and structured training.

- Standard 3: (Instruction) Instruction is learner-centered, participatory and inclusive.

- Standard 4: (Assessment) Appropriate methods are used to evaluate and validate learning achievements.

j) Teachers and other Education Personnel

- Standard 1: (Recruitment and selection) Sufficient and qualified teachers and other education personnel are recruited through a participatory and transparent process based on selection criteria that reflect diversity and equity.

- Standard 2: (Conditions of work) Teachers and other education staff have clearly defined conditions of work, follow a code of conduct and are appropriately compensated.

- Standard 3: (Support and supervision) Supervision and support mechanisms are established for teachers and other education staff, and are used on a regular basis.

k) Education Policy and Coordination

- Standard 1: (Policy Formulation and enactment) Education authorities prioritize free access to schooling for all, and enact flexible policies to promote inclusion and education quality.

- Standard 2: (Planning and Implementation) Emergency ed. takes into account nat’l and int’l educational policies and standards and the learning needs of affected populations.

- Standard 3: (Coordination) Transparent coordination mechanism for emergency ed. Activities, including effective information sharing between stakeholders.

l)  INEE Minimum Standards:

- Tool to improve the effectiveness and quality of education in emergency situations

- Commitment to accountability

- The 5 categories are interdependent and must be applied based on the specific context

- Based on the principle that affected populations have the right to life with dignity

* Standards above were prepared by more than 2250 participants from local to global level.

7. Group work – Lessons Learned/Best Practices – Sweta Shah and George Murray

- Review the education cluster’s experience for the 2008 floods in the Koshi region and Mid and Far West regions

- Reflect on what we have and have not achieved in relation to the above mentioned INEE minimum standards. These categories include:

  - Community Participation

  - Analysis

  - Access and Learning Environment

  - Teaching and Learning

  - Teachers and other Education Personnel

  - Education Policy and Coordination

- Groups were divided into 3.

1st East group (people working in or on Sunsari/Saptari/Koshi areas)

2nd West group (those working in or on Kailali, Kanchanpur, Bardiya, Banke)

3rd Kathmandu group (those working in KTM)

Group Presentations:

# KOSHI/ East Group

- Supports received from community in information collection

- Local ideas were included in the emergency situation

- Got lots of support from the locals and displaced

- Aware on the situation and dealing with the emergency situation

- Population outside the camps should also be dealt with since they are also the victims during flood

- Discussions were done on safe space and child friendly training was also conducted based on local context. Teachers were also trained on dealing with psychology trauma.

- Could not cover all the contents during the training due to time constraint.

- Actual work that had to be done in the effective area more efforts should be given in the affected area

- Children out of school before emergency situation were also enrolled in schools

- Facilitators were selected in the community keeping in mind the culture, linguistic and gender)

- Supervision was done by the camp management committee

- District Education Office should reinforce for the mobilization of regular teachers

- A monitoring team should be formed and education cluster can support in preparing the ToR.

- It is always difficult to mobilize teachers after disaster takes place. It would be appropriate to train them beforehand and prioritize it in disaster prone areas.

## KAILALI/ Western Group

- Less active participation from the communities

- Support teachers, students and parents in re-establishing the schools

- A shelter to be constructed/ identified to manage the trainings during emergency

- No standards maintained due to lack to preparations

- One shelter in one VDC. Fund collection at community level can be done.

- Assessment was done in jointly

- Data collection was done jointly by DEO and NGO

- Monitoring is being done

- Present stage is in evaluation

- Access was done partially

- Even though schools started early classes could not be conducted due to lack of learning materials

- Curriculum, teachers training, children’s assessment could not be done due to short

- Regular coordination among various stakeholders was effective period of time.

KAILALI - 2009 plans:

- Information collection at VDC level

- Keep record of contact person and contact numbers

- Identify focal person in District Education Office

- Mobilize Local level groups

- Formation of evaluation team and ensuring their participation from central to local level

- Storage of education materials, Kit box and learning materials

- Develop temporary learning centers and management of library

- Conduct teachers trainings and develop training packages. Preparation for non-formal education and multi grade education

- Volunteers and volunteer teachers

- Funds for emergency at central level and mechanisms for releasing the funds within 24 hours to local level in emergency

KATHMANDU

- Coordination between government and I/NGOs

- Activation of education clusters

- Joint field visits

- Coordination meeting among different stakeholders and information sharing

### Future Plans – Kathmandu Group

- Policy formation and plan preparation (From ECD age to upper level children)

- Prepare sector plans (On EiE)

- Inter-ministerial coordination

- Media sensitization on facts and figures. A response body needs to be established in DoE or MoES

- Central disaster relief committee was formed under the chairperson of Home Ministry

- Volunteerism to be promoted as human resource

- Disaster Relief policy 1982 should be managed in EiE including construction

- Collection of reusable of educational materials and store in Resource Centers, management of teachers and learning materials

- Prepare policy guidelines for teachers management during emergency

- Alternative management of shelters for victims instead of schools

- Develop media response body

.

8. Response Planning and Preparedness Implementation – George Murray

a) Develop response plans

- Define sector / cluster specific principles and operational objectives

- Define individual (organization) and collective actions to meet the sector / cluster objectives

- Define sector / cluster preparedness, assessment and response actions

- Consolidate and review planning outputs

b) Define Individual and Collective Actions

- Specialized roles

- Common standards

- Current capacities

- Gaps between capacity and the scale of the emergency

- Approach to needs assessment

- Information management mechanisms

- Monitoring and reporting tools

c) Develop a Strategy for Initial Assessment

- Planning for initial assessment should include:

    - Identification of organizations that will participate;

    - Agreement on specific rapid assessment tools;

    - Discussion of how sector / cluster assessment information will be collated and shared with others.

d) Consolidate and Review All Planning Outputs

- Analyze consolidated response plans for:

- Consistency with initial planning assumptions;

- Consistency with the overall humanitarian strategy and objectives;

- Gaps or overlooked issues;

- Duplication of common services or activities between sectors / clusters;

- Appropriate allocation of resources to priorities;

- Integration of cross-cutting concerns such as protection, gender, human rights, etc.

  - Sample Plan

- Executive Summary

- Hazard & Risk Analysis

  - Brief summary of the hazards and risks analyzed during the contingency planning process.

- Scenarios & Planning Assumptions

  - Brief summary of agreed scenarios and planning assumptions that define the parameters of the contingency plan.

- Objectives & Strategies

  - Concise statements of objectives, strategies and guiding principles.

- Overall Management & Coordination Arrangements

  - Clusters established and designated lead organizations.

  - Diagram of coordination mechanisms.

  - Arrangement for appeals and funding.

  - Information management arrangements

  - Cross-cutting issues.

- Summary of Sector / Cluster Response Plans

  - Outline of participation in sectors.

  - Objectives and response actions.

  - Gap analysis.

  - Standards guiding response.

- Preparedness Actions

  - Agreed priority preparedness actions.

  - Preparedness actions by sector.

- Annexes

  - Summaries of sector plans.

  - Detailed schedule for implementation of preparedness actions.

  - Schedule for review and updating contingency plans.

  - Terms of Reference for sector / cluster groups.

  - Implementing Preparedness

- To ensure continuous implementation and follow up to the contingency planning process.

- Implement a minimum set of priority preparedness actions

- Establish systems for monitoring early warning indicators

- Consolidate preparedness, assessment and response actions and division of responsibility

- Review, test & update plan

g)

Contingency Planning is about saving lives by enhancing the quality of humanitarian response

It is not a theoretical exercise:

If you do not implement preparedness, contingency planning will not save lives.

h) Preparedness Actions

Actions:

A minimum set of priority preparedness actions should be identified and agreed to by all agencies / organizations.

Examples of preparedness actions:

- Training humanitarian staff and partners in rapid needs assessment techniques

- Collecting baseline, disaggregated data sets

- Carrying out security assessment

- Identifying and establishing collaborative arrangements with local implementing partners

- Raising awareness on prevention of sexual exploitation and abuse.

DAY TWO

1. Review of Day 1 – Sweta Shah

2. Group Work – Contingency Planning for 2009 (please see Contingency Planning document) – Sweta Shah, George Murray

- Split into groups based on the themes in the floods scenario of the contingency plan

  - Group 1: Cluster Management and Human Resources

  - Group 2: Rapid Education Assessment and Ongoing Assessment, Monitoring and Information Management

  - Group 3: Temporary/ Safe spaces and Psychosocial support for teachers and students

  - Group 4: Teaching/ Learning Materials

  - Group 5: Recruitment, mobilization and Training of teachers and Para-teachers

- Review the 2008 contingency plan

  - Does anything need to be added, taken out changed?

  - Which of the INEE minimum standards can be integrated or improved upon in your thematic area?

  - Will your agency take a leading or supporting role?

  - When will the work be accomplished?

3.  Advocacy message for education cluster – Sweta Shah

Why should education be prioritized? What can you say when in the field advocating for education as a priority in emergencies?

A 1-page document will be developed after collating comments from the groups. The comments of the group are listed below.

- Education provides opportunities to normalize their life

- Education provides children something to do in emergencies

- For protection – for hazards, physical protection

- Education creates a safe environment

- Education creates an arena for communication

- Arena to socialize / common venue

- Promotes personal hygiene, sanitation and health

- Education for mutual trust, mutual respect, mutual help, mutual understanding , to ensure  co work environment

- Education is the rights of children

- Continuity of education during disaster is important

- Alleviates and mitigates trauma (psychosocial disorders)

- Education plays a role is social harmony

- Ensure no gap between knowledge and implementation

- Education enhances unity

- Education knows no age boundaries

- Education on disaster promotes disaster preparedness and safety

- Education overcomes discrimination and social exclusion

- education supports daily living skills

- Education halts exploitation at the community level

- Children want education

4. Activity and Action Plan – Sweta Shah, George Murray

All comments and feedback have been integrated into the Contingency Planning document.