## Slide 1: Contingency Planning
Notes: <number>

## Slide 2: Objectives
Understand what is contingency planning and why it is important.
Understand the key components of the contingency planning process.
Understand how to develop a contingency planning document.
Begin the contingency planning process.
INEE and Education Cluster

## Slide 3
Often led by technical clusters (i.e. Education cluster)
Should include active participation and leadership of government ministry (i.e. Ministry of Education)
One of the key outputs of contingency planning is the development of a contingency planning document.
Contingency planning is a an on-going process led by key stakeholders to reflect upon and prepare for various emergency scenarios
What is Contingency Planning?
INEE and Education Cluster
Notes: The plan should be reviewed and updated regularly, at least annually.
The plan itself serves as a record of agreements reached during the contingency planning process, and can be used as a basis for managing follow-up actions and communicating results to others.
- For the education sector, the Education cluster, including the Ministry of Education, have usually led this process.
<number>

## Slide 4: Why Contingency Planning?
It’s a key to preparing for
emergencies.
It provides an opportunity to
identify constraints and focus on
operational issues prior to the
on-set of a crisis.
Strengthens coordination and
relationships by working together to conduct this process.
A common understanding of agencies’ capacities and challenges helps facilitate effective collaboration in a crisis. Ensures no overlap or gap of services provided.
INEE and Education Cluster

## Slide 5: Who should be involved?
All those required to work together in the event of an emergency
  Should also include coordination with other sectors (e.g. WASH, Child Protection)
Those affected by the response (e.g. students, teachers)
Education authorities at the national and local levels
Experts on areas covered in the plan (e.g. engineers to help with school re-construction)
INEE and Education Cluster

## Slide 6: Uses of a Contingency plan
Capacity Development
Monitoring Preparedness
Emergency Risk Reduction
Has agreed upon capacity development plan
- Increase participants’ awareness of, access to, and use of existing tools (e.g. best practices, templates)
- A framework for monitoring progress, outcomes, and impact of preparedness measures.
- Analyse risks, vulnerability and response capacity
- Identify preparedness measures
- Provides a joint platform for involved actors
Notes: Though the aim with the planning is not a written plan, a written document can be used in a number of ways.
<number>

## Slide 7: Uses of a Contingency plan
Communication and Advocacy
Mobilising and managing resources
Analysis, planning and coordination provides a good platform for communicating and advocating on the importance of education in emergency preparedness initiatives.
- Coherent and well informed plans are a good foundation for dialogue with donors
Notes: Though the aim with the planning is not a written plan, a written document can be used in a number of ways.
<number>

## Slide 8: Contingency planning process
Examples:
- Flooding in x region
- Potential ethnic violence in x region
Examples:
25% of school-aged population affected
X schools damaged
Contingency planning template
INEE Minimum Standards for education
Preparedness checklist
Implementation mid-term review
3Ws – Who does what where (Capacity Mapping)
- Lessons Learned Exercise
Notes: Contingency planning is a process that takes time. It can start off as an education cluster meeting, lead into a larger workshop or it can be conducted over a period of a 3 day workshop.
It is a continuous process of analyzing contexts, revising plans and implementing preparedness.
Contingency planning is NOT a process to produce a written plan. It is a process to ensure and enhance proper preparedness, of which a written plan is just one useful element.
<number>

## Slide 9: EXERCISE: Lessons Learned
Directions:
Split the participants into 5 groups of approximately 5-6 people.
Each group will work on 2 of the INEE Minimum Standards domains
  Group 1: Foundational Standards and Access and Learning Environment
  Group 2: Access and Learning Environment and Teaching and Learning
  Group 3: Teaching and Learning and Teachers and other Education Personnel
  Group 4: Teachers and other Educational Personnel and Education Policy
  Group 5: Education Policy and Foundational Standards
Reflect upon and answer the following questions (write response on flip chart) (60 minutes)
  Did the previous emergency response meet the standards in that domain?
  If yes, could this be improved upon? How?
  If no, do they think it is realistic in the context to reach the standard if there were another emergency? How?
4. Gallery Walk (20 minutes)
INEE and Education Cluster

## Slide 10: EXERCISE: Developing a Contingency Plan
Directions:
Split the participants into 6 groups based on the following categories:
Group 1: Assessment, Monitoring, Evaluation and Information Management
Group 2: Cluster coordination/management and Human Resources
Group 3: Teacher Recruitment, Mobilisation, Training, Compensation
Group 4: Temporary Learning Spaces and Psychosocial support strategies
Group 5: Education supplies and logistics and Emergency Education Curricula (formal and non-formal education)
Group 6: Rehabilitation and Construction of schools and Resumption of formal education
The groups will have 90 minutes to complete the Contingency plan worksheet for their group (see Handout 9.1). This includes completing the plan for preparedness and response.
3. Large group presentation and discussion (60 minutes): Each group presents their ideas to the rest of the group.
INEE and Education Cluster

## Slide 11: Contingency planning worksheet
INEE and Education Cluster
Activity category | Response activity | Preparedness activity | Link with INEE Minimum Standard | By Whom | By When
Teacher Recruitment, Mobilisation, Training and Compensation |  |  |  |  | 
Education supplies and logistics and Emergency Education Curricula |  |  |  |  |