Education Cluster

Emergencies Contingency Plan 2009

Nepal

Designed: 23 June 2009

TABLE OF CONTENTS

I.  Introduction	3

II.  Objectives	3

III.  Education Cluster Members, Management and Operations	3

IV.  The Emergency Scenarios	4

V.  Emergency Response General Principles and Procedures	6

VI.  Early Recovery Activities	6

VII.  Additional Personnel Requirements	7

VIII.  Additional Material and Financial Requirements	7

IX.  Recovery and Reconstruction Activities	7

X.  2009 Detailed National Contingency Plan for Seasonal Floods/Landslides Scenario	8

Annex 1. Education Cluster Members	17

# I.  Introduction

The purpose of this Contingency Plan document is to prepare the Education Cluster for a more effective response to the education needs during emergencies.  This national plan was developed collaboratively by members of the Education Cluster during a two day Contingency Planning workshop held in June 2009 and takes into account lessons learned from previous emergency responses. Following the national level Education Contingency Plan, the District level Education clusters participated in a multi-sectoral District Contingency Planning (DCP) process. This was piloted in 2009 in seven districts.

Nepal is at risk for the following types of emergencies: 1) seasonal floods/landslides, 2) large scale earthquake in the Kathmandu Valley, 3) small scale earthquake outside of the Kathmandu valley, 4) Political events causing a humanitarian crisis. In the past few years, seasonal floods/landslides have been the greatest threat in Nepal. Thus, the details of the plan are specific for the situation of seasonal floods/landslides, however the key principles and activities would be the same in the event of an emergency based on the other scenarios.

# II.  Objectives

- Overall Objective

To ensure immediate and continued access to quality education of all affected children aged 0 to 18 years in a safe environment necessary to develop, protect and facilitate a return to normality and stability.

- Specific Objectives

  - To provide support to the Government of Nepal and local level stakeholders in ensuring continuity of quality education to children and teachers affected by natural disasters and conflicts and provide them with safe teaching-learning environment.

  - To ensure effective coordination and monitoring and information sharing among cluster members necessary to facilitate effective emergency response.

  - To strengthen the capacities of stakeholders as first responders in emergency situations.

  - To ensure the conduct of rapid and ongoing education assessment and delivery of appropriate response as guided by UNICEF’s Core Commitments to Children in Emergencies for Education and the Inter-agency Network for Education in Emergencies (INEE) Minimum Standards.

  - To establish and strengthen strategic partnerships and linkages with other partners/clusters in order to respond effectively to emergency situations.

# III.  Education Cluster Members, Management and Operations

Cluster Leads: UNICEF, Department of Education (Ministry of Education), Save the Children

Other Members:  National Teacher’s Union, World Education, World Vision, Plan, TPO, N-PABSON, PABSON, Setu Guras, Education Pages, Nepal Red Cross Society, Education Journalist Group

###### Permanent Cluster Operations

The Department of Education (DoE), together with UNICEF and Save the Children Alliance (SC), will coordinate and provide overall leadership and strategic direction of the emergency preparedness and response at the national level.  They will ensure that education is prioritized in emergencies and advocate to the Ministry of Education to establish 1) an Education Endowment fund for emergencies, 2) establish an emergencies unit within the Department of Education, and 3) assign a focal point at the national and district levels to support emergency preparedness, response and recovery.  At the district levels, the Ministry of Education will be represented by the District Education Office (DEO).  The cluster leads will ensure full participation of other cluster members.  The cluster should advocate to the other clusters and ensure inter-sectoral linkages are made between Education and other clusters.  The cluster leads bear the responsibility for the overall cluster. Under normal circumstances, when there is no emergency, the cluster leads should meet monthly while all of the cluster members should meet bi-monthly to update each other on any education issues which have arisen or are outstanding.

###### Emergency Cluster Operations

In the event of an emergency, at the national level, the Education Cluster leads, should call for meetings as required to respond. The cluster leads should also call for meetings at the district levels. The Department of Education will facilitate these meetings at the national level while the District Education Office will facilitate these meetings at the district levels. Both the DOE and DEO will call the meetings and invite cluster members. UNICEF and SC as co-cluster leads should support the facilitation of all of these meetings. UNICEF, SC as Education Cluster leads will attend the IASC emergency meetings called by the HC during an emergency, where all available information about the emergency, including location, damage and needs, will be distributed. DOE will attend these meetings if the emergencies focal point is available. Following these meetings, Education Cluster meetings should be called and members should be updated. At the district level, meetings will be held at the office of the DEO, weekly or daily, depending on the scale of the emergency. Education Cluster members at the district level should also attend meetings called by the District Disaster Relief Committee DDRC).

# IV.  The Emergency Scenarios

- Floods/Landslides

Floods and landslides pose the greatest threat in Nepal as climate change has impacted the arrival of seasonal monsoon rains. In August 2008, the Koshi River, with one of the largest river basins in Asia, breached its eastern embankment, inundating four Village Development Committees (VDCs) in the district of Sunsari.  The effects of this flooding was widespread, as the government estimated that between 70,000 and 100,000 people were initially affected, with extensive displacement from the flood-affected areas into neighboring VDCs in both Sunsari and Saptari districts.  As the repair to the embankment is underway, there is a belief that the type of flooding that was experienced could occur once again due to issues with embankment construction and changing river morphology. Further, Nepal faced flash floods and landslides in the districts of Bardiya, Banke, Kailali and Kanchanpur, affecting thousands more people.

Estimated Affected Population:

Moderate Flooding: 6,000 - 12,000 families (approximately 36,000 – 72,000 people)

Severe Flooding: exceeding 60,000 families (approximately 360,000 people)

Disaggregated by sex and age:

# children:

3-18 years	35%	126,000

3-5 years	6%	7560

6-9 years	14%	17,640

10-1 years	15%	18,900

Boys 3-18: 63,000 (50%)

Girls 3-18: 63,000 (50%)

Major Constraints: access to VDCs

- Large Earthquake in Kathmandu Valley

Baseline data:

40,000 dead

95,000 injured

600,000-900,000 homeless, displaced

60% schools destroyed

Disaggregated by sex and age:

# children: ages 3-18

3-18 years	35%	315,000

3-5 years	6%	18,900

6-9 years	14%	44,100

10-18 years	15%	47,250

Boys 3-18: 157,500 (50%)

Girls 3-18: 157,500 (50%)

Major Constraints:

- Logistics

- Heavily reliant on support from surrounding region and HQ

- Financial and human resources

- Small Earthquake outside of Kathmandu Valley

Baseline data:

53,000 injured;  # of Displaced people: 150,000

Disaggregated by sex and age:

# children: ages 3-18

3-18 years	35%	52,500

3-5 years	6%	3,150

6-9 years	14%	7,350

10-18 years	15%	26,250

Boys 3-18: 26,250 (50%)

Girls 3-18: 26,250 (50%)

- Political events causing a humanitarian crisis

While the decade long war in Nepal has ended

Baseline data:  1.2 million affected

Impact: School closures as a result of strikes and security issues, displacement as a result of destruction of houses, schools, security threats

Disaggregated by sex and age:

# children: ages 3-18

3-18 years	35%	420,000

3-5 years	6%	77,000

6-9 years	14%	192,000

10-18 years	15%	193,000

Major Constraints: political, security, access

# V.  Emergency Response General Principles and Procedures

- The Education Cluster will convene based on any or combination of the following trigger mechanisms: 1) the Government of Nepal declares a state of national emergency; 2) initial media or partner feedback on the extent and impact of the emergency; 3) the UN humanitarian coordinator  assembles the clusters to be prepared to respond.

- The Nepal Red Cross will conduct the Initial Rapid Assessment to survey the general situation of the emergency within the first 24 hours.

- Within the first 72 hours, the Multi-sectoral Initial Rapid Assessment (MIRA) team will be mobilized to conduct a technical rapid assessment. Education is a key component of this assessment form.

- If a more detailed Education assessment is required, a team of Education specialists will conduct this.

- Restoration of schooling to the affected children will be immediately carried out through 1) the rehabilitation of usable classrooms in affected areas, 2) the establishment of child friendly spaces or safe spaces in affected or IDP areas for ECD and other activities for younger children and 3) Temporary Learning Spaces (TLC) for school going children.  The education cluster will coordinate with WASH for the provision of girl friendly water and sanitation facilities and ensuring water points are nearby.

- Teaching/learning materials and school supplies, including pre-positioned Child kits, will be provided to the affected school-aged children and teachers. Teachers will be mobilized and trained as needed to provide education.

- Psychosocial support and increased protection from various impacts of the disaster will be carried out among a large proportion of affected children in collaboration with the child protection cluster in the child friendly spaces.  Teachers will be trained to deliver classroom and recreational activities to address psychosocial impacts of the emergency. Teachers will also be provided with information on gender based violence and care for survivors.

- Priority will be given to the most vulnerable and affected areas and schools in terms of distribution of educational resources. Children from host communities will also be supported to ensure there is no tension between host and displaced populations. Schools in host communities will also be supported so they can support additional displaced children. This support will include teaching and learning materials, additional teachers, and school furniture.

- NGOs, community members and organizations of the affected population will be mobilized as implementing partners in the field based on the following criteria: 1) operational in affected area; 2) experience working in emergency and education response; 3) demonstration of good track record.

# VI.  Early Recovery Activities

- When conditions permit, rehabilitation and repair of school structures damaged by disaster will be undertaken by the DOE and DEO.

- Learning process of school-aged children will be sustained through the provision of teaching/learning materials, provision of temporary learning and safe spaces as needed, and recruitment of temporary teachers as needed. Each district’s DEO will be responsible for the recruitment of teachers while all cluster members will jointly provide teaching/learning materials, temporary learning and safe spaces.

- Regular ongoing assessment and monitoring of the situation will be undertaken by the DEO and information will be shared with all cluster partners in order to adjust education responses.

- Resumption of quality educational activities in literacy and life skills, HIV, prevention of sexual exploitation, gender rights, and hygiene will be promoted by all Education cluster members in coordination with the Protection (ie. Child Protection and Gender Based Violence), WASH and Health  clusters.

# VII.  Additional Personnel Requirements

- In the event of a large scale emergency affecting over 100,000 people, one or more international education emergency professions may be mobilized either through secondment or recruiting. National staff may need to be recruited to work in field or hub locations. UNICEF and Save the Children will coordinate human resource needs and recruitment with the DOE.

- Volunteer teachers may have to be recruited to compensate for the loss or displacement of affected teachers. The DOE will take responsibility to lead in the recruitment process.

# VIII.  Additional Material and Financial Requirements

- Electronic copies of all textbooks need to be made and stored in safe places based on type of disaster in order to reproduce textbooks as needed in the event of a large scale disaster.  DOE will ensure that electronic and camera ready textbooks and accelerated learning textbooks are ready and safeguarded in the event of an emergency. As part of the preparation, these materials should be sent to the DEO. UNICEF/SC will support the DOE and DEO.

- Long term agreements with suppliers for tents, tarpaulins, and school supplies will be negotiated by the cluster members, and suppliers identified based on the different contingencies. For a major earthquake in the Kathmandu Valley, suppliers from outside the Valley will be contacted.

- In the event that textbooks are not available, emergency education materials in literacy, numeracy and life skills need to be translated into Nepali and electronic and hard copies safeguarded for printing and distribution. The DOE will lead this effort while UNICEF/SC will support this effort.

- Psychosocial classroom teaching and learning materials will be available on CDs and safeguarded, and printing arrangements made to make these materials available.  UNICEF/SC will provide and safeguard materials for printing and distribution.

- Classroom materials in disaster risk reduction for earthquakes and floods will be incorporated into the national curriculum and introduced in schools in schools in vulnerable regions.  The Curriculum Development Centre has taken responsibility for this. The Education cluster will also coordinate with the Ministry of Home and its departments (ie. The National Disaster Relief Committee and District Disaster Relief Committee).

- UNICEF and SC will coordinate all cluster members and conduct emergency appeals to raise funds to finance a portion of the emergency education response through their fundraising channels.

# IX.  Recovery and Reconstruction Activities

- The DEO will be responsible for overall longer term recovery and reconstruction of damaged or weakened education systems.

- Cluster members will work closely with the DEO to ensure rehabilitation and reconstruction of schools by providing financial and technical support.

- Temporary and volunteer teachers will be compensated by the DOE.

- Policies will be established regarding future certification opportunities for temporary teachers trained during teacher mobilization phase.

# X.  2009 Detailed National Contingency Plan for Seasonal Floods/Landslides Scenario

| Scenario | Response | Preparedness, Response and Recovery Activities | By Whom | By When |
| --- | --- | --- | --- | --- |
| 1. SEASONAL FLOODING AND LANDSLIDES Baseline data: 400,000 Moderate: 6,000 - 12,000 families 36,000 – 72,000 people Severe: exceeding 60,000 families 360,000 Disaggregated by sex and age: # children:126,000 ages 3-18 (35%) 3-5: 7560 (6 %) 6-9: 17,640 (14%) 10-18: 18,900 (15%) Boys 3-18: 63,000 Girls 3-18: 63,000 Total 0-3 years children are 52% 0-3 years 7% 3-5 years 9% 5-9 years 15% 10-18 years 21% Constraints: access | Cluster Management: Lead at the National level: UNICEF, Department of Education (DOE), Save the Children (SC) Lead at the District Level: DEO, DDRC, UNICEF field office, Save the Children field office | MoU between the 3 cluster management team members (DEO, UNICEF, SC) signed | Lead: Bishnu Devkota, Department of Education (DOE) Support: UNICEF, SC | 7 July 2009 |
|  |  | Mapping at national and selected district level of 1) vulnerable populations 2) education actors 3) number of schools and ECD centers (direct and indirect impacted). Teacher’s Union to gain the support of the local community. | Lead: DEO, DoE Support: Teacher’s Union, UN and NGO field office staff | End July 2009 |
|  |  | Identify and train focal point of DEO and relevant partners at the district level on Education in Emergencies. | Lead: UNICEF, SC | End August 2009 |
|  |  | Conduct a Training of Trainers (TOT) on Education in Emergencies (EiE). | Lead: UNICEF, SC | End August 2009 |
|  |  | Establish a roster of trainers from the Education Cluster that can provide EiE training at the district levels. | Lead: UNICEF | End August 2009 |
|  |  | Establish and functionalize the communication network from school to district and district to national, including incident reporting mechanisms within timeline established and functional | Lead: DG, DoE | mid July 2009 |
|  |  | Call Cluster Meeting in 24 hours both at national and district level and establish meeting schedule. | Lead: UNICEF, SC Support: DoE, DEO | Within 24 hours of an emergency |
|  |  | Call national level cluster meetings every 2 months. | Lead: DOE | Immediately |
|  |  | Call Cluster leads’ meeting every month. | Lead: UNICEF | Immediately |
|  |  | Activate Communication network and identify ways of communicating | Lead: SC | 30 June 2009 |
|  |  | Review Contingency Plan for 2010. | Lead: DoE | Jan. of every year |
|  | Human Resources Needed: (staff from the government, INGO, NGO and UN) | Mapping of relevant organizations and their staff capacity. | Each agency assess their own staff and needs. | 28 June 2009 |
|  |  | Identify capacity gaps and provide a list of staff that require training to UNICEF. | Each agency assess their staff capacity and send a list to UNICEF. | 1 July 2009 |
|  |  | DOE should designate a focal point for emergencies at the KTM level and DEO should designate a focal point for emergencies at the district level. | Lead: DOE for KTM Lead: DEO for each district | 30 June 2009 |
|  |  | DOE to formulate a list of focal points and the training status | Lead: DOE | 28 June 2009 |
|  |  | Mobilize identified staff for immediate response | Each agency | At the on-set of an emergency |
|  |  | Contract staff for identified capacity gaps | Each agency based on need | July 2009-August 2009 |
|  | Assessment: Lead for Initial Rapid Assessment (first 72 hours): Red Cross Lead for Assessment after 72 hours: | Identify key people to conduct rapid assessment and support deployment as soon as possible. | Each agency | 30 June 2009 |
|  |  | Participate in MIRA (Multi-sectoral Rapid Assessment) | Lead: OCHA | 22-23 June 2009 |
|  |  | MIRA district Orientations in 7 priority districts. | Lead: UNICEF/SC | End July 2009 |
|  |  | Update the assessment forms | Lead: World Education | 30 June 2009 |
|  |  | Collate all date from the assessment forms | Lead: World Education | After the on-set of the emergency |
|  | Monitoring, Evaluation and Information Management: | Joint technical field monitoring. | Lead: DEO Support: Education cluster agencies working in the district | Every 2 weeks after the emergency begins |
|  |  | Formulate first report on educational impact based on available data, share with relevant partners including media and establish schedule for situation reports | Lead: DEO Support: | Every 2 weeks after the emergency begins |
|  |  | Local Monitoring committee formation & supervision. This local monitoring committee should include representation of the district (ie. men, women, youth, boys, girls) | Lead: DEO Support: | mid July 2009 |
|  |  | Evaluation/ impact study of temporary learning spaces/ safe spaces | Lead: SC | September - October 2009 |
|  |  | Monitoring checklist to be developed and used by local monitoring committee and government, INGO, UN, NGOs. | Lead: World Education | mid July 2009 |
|  |  | Orientation for local monitoring committee on how to use the monitoring check-list. | Lead: DEO of each district | End July 2009 |
|  | Government Policy: Lead at the National level: DOE Lead at the District level: DEO | DEO should ensure that emergency preparedness and response should be reflected in Annual Strategic Implementation plan (ASIP), Education Act, Work Plan and Budget and education guidelines through a chapter education in emergencies | Lead: Hari Lamsal, DoE | 15 July 2009 |
|  |  | Propose to Ministry of Finance to revise existing procedure of budget use according to the strict allocation | Lead: Director General, DoE Support: UNICEF, SC | 30 June 2009 |
|  |  | Establish Education Endowment fund (contingency lump sum) for Emergency and prepare guideline for use (within jurisdiction of the MoE, hence linked to Education Act) at the national and district level | Lead: Director General, DoE incorporating in the Education Act Amendment | Next Winter (Dec. 2009- Jan. 2010) |
|  |  | Influence Ministry of Home Affairs to include education in emergencies in National Disaster Management Plan and in the District Disaster Management Plan and DDRC | Lead: UNICEF, SC Support: Director General, DoE | October 2009 |
|  |  | Advocate for the inclusion of EiE into the School Sector Reform Plan (SSRP) | Lead: DoE, UNICEF, SC | 3 times per year |
|  | Temporary Learning Spaces/Safe Spaces: | Orientation on how to use toys and materials provided for temporary learning space/ safe space | Lead: SC | As soon as spaces are set up |
|  |  | Tent and Tarpaulin stock | Lead: UNICEF | mid July 2009 |
|  |  | Vendor identify for school kit | Lead: UNICEF | 30 June 2009 |
|  |  | Safe space fixing group preparation | Lead: DEO | mid July 2009 |
|  |  | Pre-monsoon response partner meeting for common understanding | Lead: DEO | mid July 2009 |
|  |  | Response partners capacity building training | Lead: SC | mid July 2009 |
|  |  | Safe space guidelines revision and translation | Lead: SC | mid July 2009 |
|  |  | Safe spaces manual needs to be authorized and translated into Nepali | Lead: SC | mid July 2009 |
|  |  | Facilitators training content design | Lead: SC | mid July 2009 |
|  |  | Safe Space facilitator training at the district level | Lead: SC | mid July 2009 |
|  |  | Safe space manual translation and authorize | Lead: SC | mid July 2009 |
|  |  | Safe space operation/ management committee formation | Lead: SC | mid July 2009 |
|  |  | Deploy the construction materials for Temporary Learning Spaces | Lead: UNICEF | Immediately at the on-set of the emergency |
|  | Psychosocial support for teachers and students: | Identify a list of children and adults in need of counselling services (those identified from the Child Friendly Spaces) | Lead: SC, TPO | On-going after the emergency |
|  |  | Develop a referral mechanism with the Child Protection cluster to refer those in need of counseling | Lead: SC | mid July 2009 |
|  |  | Psychosocial teacher and safe space facilitator training of trainers | Lead: UNICEF Support: SC | Next year |
|  |  | Psychosocial teacher and safe space facilitator training | Lead: UNICEF Support: SC | Next year |
|  | Teacher Mobilization, Recruitment and Training: | Form a committee for teacher mobilization, recruitment and training at the district level. Ensure representation from females. | Lead: DEO Support: Teacher’s Union and other Partners in the district | mid July 2009 |
|  |  | Recruitment of volunteer teachers (Retired and license holders in priority). There should be both male and female teachers. | Lead: DEO Support: Teacher’s Union | mid July 2009 |
|  |  | Mobilize teachers from neighbouring schools | Lead: Teacher’s Union | As needed during the emergency |
|  |  | Prepare roster of volunteer teachers (both male and female). | Lead: DEO Support: Teacher’s Union | mid July 2009 |
|  |  | Prepare a teacher training module/manual focused on emergency education (ie. including the special needs of vulnerable groups such as girls). | Lead: UNICEF | mid July 2009 |
|  |  | Training of Trainers for teachers on EiE in the most vulnerable flood prone districts | Lead: UNICEF/SC Support: DEO | Next year |
|  |  | Train teachers on the emergency roster in EiE at the district Resource Centre | Lead: DEO Support: UNICEF/SC | Next year |
|  |  | Role of SMC and PTA can be defined by mobilizing them in reporting and providing information from local level to MoES. | Lead: DoE Support: DEO | mid July 2009 |
|  | Teaching/Learning Materials: (Deploy teaching materials to temporary learning/safe spaces or temporary schools) | Text books stockpiled by DOE and accelerated learning textbooks at primary, lower secondary and secondary stockpiled by DOE | Lead: DoE | mid July 2009 |
|  |  | DOE orders printing of additional textbooks. | Lead: DoE | mid July 2009 |
|  |  | Photocopy extra copies of textbooks, curriculum and teacher’s guide and send them to DEO. | Lead: DoE | mid July 2009 |
|  |  | Age wise learning materials stock pile (3-5, 6-12, 13-18 years) | Lead: UNICEF | mid July 2009 |
|  |  | School in a box kits prepared and ready to be deployed | Lead: UNICEF | mid July 2009 |
|  |  | Stockpile Early Childhood Development (ECD) kits | Lead: UNICEF | mid July 2009 |
|  |  | Prepare Life Skills materials for deployment (including gender based violence) | Lead: UNICEF | mid July 2009 |
|  |  | Parenting Education kit packs | Lead: Seto Guransh Support: | mid July 2009 |
|  |  | Toys for children below 3 years of age | Lead: Seto Guransh Support: SC, UNICEF | mid July 2009 |
|  |  | Recreational materials | Lead: Seto Guransh Support: SC | mid July 2009 |
|  |  | DOE approval on he translated materials. | Lead: SC | mid July 2009 |
|  | Recovery and Reconstruction: | Conduct an assessment of school and equipment damage with individual school assessment tool | Lead: SC Partners: | October-November 2009 |
|  |  | Collect and share data | Lead: SC Partners: | October-November 2009 |
|  |  | Seek funds for rehabilitation and reconstruction | Lead: UNICEF, SC Partners: | October-November 2009 |
|  |  | School reconstruction | Lead: SC Partners: | November 2009 onwards |

# Annex 1. Education Cluster Members

|  | NAME OF PARTICIPANTS | DISTRICT | Email | Telephone |
| --- | --- | --- | --- | --- |
| 1 | Agatha Thapa | Lalitpur | agatha@mail.com.np ; setoguransncds@ntc.net.np | 9851027838 |
| 2 | Anjalee Thakali | Kathmandu | anjalee.shakya@savethechildren.org.np |  |
| 3 | B. K. Devkota | Bhaktapur |  | 9841754292 |
| 4 | Bhoj Bdr Balaya | Bhaktapur | balayarab@hotmail.com |  |
| 5 | Bhola Prasad Sahal | Kathmandu | bhola.dahal@savethechildren.org.np |  |
| 6 | Damodar Regmi | Bhaktapur | damodar.regmi@gmail.com | 9841340598/ 6637677 |
| 7 | Deergha Narayan Shrestha | Kathmandu | deergha@hotmail.com |  |
| 8 | Dol Raj Panday | Surkhet | panday_dr@yahoo.com | 9845051522 |
| 9 | Ganesh Bdr Singh | Kailali | singhganesh45@gmail.com | 9858420593 |
| 10 | Ganesh Khatri | Kathmandu |  | 9849231298 |
| 11 | Hari Pd Lamsal | Sanothimi | hlamsal@gmail.com | 9841343957 |
| 12 | Helen Sherpa | Kathmandu | helen@wei.org.np |  |
| 13 | Hemant Kumar Singh | Sunsari | hemant_ktm@hotmail.com | 9852048157 |
| 16 | Jagdish Oli | Kathmandu |  | 9841461414 |
| 17 | Khagaraj Paudyal | Bhaktapur | paudyal_khaga@yahoo.com | 9841394234 |
| 18 | Khila Nath Niraula | Morang | khila.niraula@savethechildren.org.np |  |
| 19 | Krishna Hari Koirala | Kathmandu | krishnahari.koirala@nrcs.org; jrc@nrcs.org | 9851019497 |
| 20 | Krishna Pd Pokharel | Dhankuta | kppokhareldkt@gmail.com | 9842029828 |
| 21 | Lieke van de Wiel | Kathmandu | lvandewiel@unicef.org | 5523200 ext. 1115; 9851107905 |
| 22 | Mahanta Babu Maharjan | Morang | mahanta_babu.maharjan@plan-international.org | 98412151782 |
| 23 | Meghanath sharma | Kathmandu | meghanathsharma@gmail.com | 9841442470, 6635134 |
| 24 | Mahashram Sharma | Bhaktapur |  |  |
| 25 | Narmaya Thapa | Kathmandu | narmaya.thapa@savethechildren.org.np |  |
| 26 | Nirmala Devi Mainali | Bhaktapur | nirmaladm@gmail.com | 9841724493 |
| 27 | Padam Pd Pande | Syangja |  | 9741050232 |
| 28 | Prakash Singh Adhikari |  | ifcd@mcmail.com.np | 9851038465 |
| 29 | Rameshwar Khatri | Kathmandu |  | 9841730134 |
| 30 | Sabina Joshi | Kathmandu | sajoshi@unicef.org | 977-1-5523200 , Ext: 1116 |
| 31 | Sharda Basnet |  | sharda.basnet@savethechildren.org.np |  |
| 32 | Suka Dev Nepal | Bhaktapur | sd_nepal@yahoo.com | 9741090605 |
| 33 | Sweta Shah | Kathmandu | sshah1999@hotmail.com | 9849204696 |
| 34 | Sudarshan Sigdel | Kathmandu |  | 9841528710 |
| 35 | Tilak Kunwar | Achham |  | 9741119297 |
| 36 | Yadav KC | Sunsari | ykc@unicef.org |  |
| 37 | Rajendra Shakya | Kathmandu | rshakya@unicef.org | 1-5523200 (ext 1125); 9851107902 |
| 38 | Rohit Pradhan | Kathmandu | rohit_pradhan@wvi.org |  |
| 39 | Asim Shrestha | Kathmandu | ashrestha@unicef.org |  |
| 40 | Mahesh Bist | Kathmandu | mahesh_bist@wvi.org |  |
| 41 | Tap Raj Pant | Kathmandu | tr.pant@unesco.org |  |
| 42 | Prem Aryal | Kathmandu | prem.aryal@plan-international.org |  |
| 43 | Mukti Pokharel | Kathmandu | mukti.pokharel@nrcs.org |  |
| 44 | Shyam Jnavaly | Kathmandu | shyam.jnavaly@actionaid.org |  |

The following seven districts were identified to pilot District level multi-sectoral contingency planning. These districts include: Banke, Kailali, Sunsari, Saptari, Sarlahi, Nawalparasi and Kapilvastu.

The Education Cluster at the national level will provide various educational services for all aged children. However, the Child Protection cluster may also provide services for children from 0-5 years of age. It is important to cross-check planned activities for the aforementioned age group with the Child Protection cluster at the district level to ensure gaps are met and there is no overlap in services.

This list includes many, but not all of the members of the Education Cluster. At the district level, there may be members of the Education Cluster that are not listed here.

A full list of members and their contact information can be found in Annex 1.

The Department of Education (DoE) is one department within the Ministry of Education (MOE).  It is responsible for finalizing the annual education budget and ensuring the implementation of education activities and services. The DoE oversees the District Education Offices (DEO) throughout Nepal.

According to Save the Children’s Survey report, 2007.

Cross check with the Child Protection cluster at the district level.

Cross check with the Child Protection cluster at the district level.

Cross check with the Child Protection cluster at the district level.